____________________________________________________________________

Variation 3 to Funding Agreement for In-Service Professional Development Services Agreement

____________________________________________________________________

Ministry of Education

Teachers’ Refresher Course Committee

CW37184 (Original)

SES1637 (This variation)

Date:  									2018

# PARTIES

The Ministry of Education acting by and through the Secretary for Education, at Wellington (the Ministry)

Teachers’ Refresher Course Committee having its registered office at 221 Newlands Road, Newlands, Wellington registration no. 448987 (the Supplier)

# BACKGROUND

- The Ministry and Supplier are parties to an agreement for In-Service Professional Development Services dated 30 September 2015 (the Agreement).

- A Variation is required to extend the term of the agreement to allow the committee to deliver planned in-service courses to the sector.

- The parties wish to vary the Agreement upon the terms and conditions as detailed in this variation.

the Parties agree as follows:

# Interpretation

## Defined terms

In this variation, unless the context requires otherwise, words and expressions defined, and references construed, in the Agreement and not otherwise defined or construed in this variation will, where used in this variation, have the same meanings and constructions as those given to them in the Agreement.

## Construction

Clauses:  a reference to a clause is to a clause of this variation;

Documents:  a reference to any document, including this variation, includes a reference to that document as amended or replaced from time to time;

Headings:  headings appear as a matter of convenience and do not affect the construction of this variation;

Parties:  a reference to a party to this variation or any other document includes that party’s personal representatives/successors and permitted assigns;

Singular, Plural and Gender:  the singular includes the plural and vice versa, and words importing one gender include the other genders.

# confirmation

Except as expressly varied by this variation, all terms of the Agreement continue in full force and effect and are acknowledged and confirmed by each of the parties.

# VARIATION

With effect from signing, the Agreement is varied as follows:

  - By the deletion of 1.1 and its replacement as follows:

## “Defined terms

In this agreement, unless the context requires otherwise:

Agreement means this funding agreement and its Schedules;

Grant means the sum of $1,020,979.20 (inclusive of GST), paid in accordance with clause 4 of this Agreement;

Minister means the Minister of Education;

Term means the term of this Agreement specified in clause 3.”

3.2 	By the deletion of clause 2.1 and its replacement as follows:

“This agreement starts 1 February 2019 and continues until 31 January 2021 unless terminated earlier in accordance with this agreement or at law”

3.3	By the deletion of clause 4.1 and its replacement as follows:

“The Ministry will pay the Grant in instalments on the dates set out below, provided:

| No. | Due Date | Amount (ex GST) |
| --- | --- | --- |
| 1 | 31 March 2019 | $110,976 |
| 2 | 15 July 2019 | $110,976 |
| 3 | 30 September 2019 | $110,976 |
| 4 | 31 January 2020 | $110,976 |
| 5 | 31 march 2020 | $110,976 |
| 6 | 15 July 2020 | $110,976 |
| 7 | 30 September 2020 | $110,976 |
| 8 | 31 January 2021 | $110,976 |
| Total |  | $887,808 |

“

3.4 	By the replacement of 5.1a into the SOW as follows:

“

| Report | Due Date | Work to be completed to achieve Milestone Deliverables |
| --- | --- | --- |
| Progress Report | 15 July 2019 | - Submit the progress report - An analysis of all completed course outcome plans and associated evaluations - A summary statement of trends risks and issues that TRCC has identified in its planned actions, including risks to the Ministry |
| Summary Report | 31 January 2020 | - Submit plan of TRCC programme for 2020 - Submit a summary report - Report on each of the tasks and relevant performance measures including: - An analysis of all completed courses and associated evaluations - Confirm delivery against service levels |
| Progress Report | 15 July 2020 | - Submit the progress report - An analysis of all completed course outcome plans and associated evaluations - A summary statement of trends risks and issues that TRCC has identified in its planned actions, including risks to the Ministry |
| Final Summary Report | 31 January 2021 | - Submit a final summary report - Report on each of the tasks and relevant performance measures including: - An analysis of all completed courses and associated evaluations - Confirm delivery against service levels |

“

# GENERAL

4.1	Counterparts

This variation may be signed in two or more counterparts all of which, when taken together, will constitute one and the same instrument.  A party to this variation may enter into it by executing any such counterpart.

4.1	Further assurances

Each party will do all things and execute all documents reasonably necessary to give effect to the terms of this variation.

EXECUTED AS A VARIATION

| Signed for and on behalf of Ministry of Education by: | Signed for and on behalf of Teachers’ Refresher Course Committee by: |
| --- | --- |
| __________________________ Signature | __________________________ Executive Officer |
| Nancy Bell | Eseta Fuli |
| __________________________ Name Date: _____________________ | __________________________ Office Manager Date:_____________________ |